## Sheet1
Internal Document Display Project
Topic | Action Item | Target Date | Status | Location | Particular Location (Under) | Change | Remarks(On Open) | Remarks(On Closing ) | Time On Open | Time on Close
Change Start Date, End Date | Required | 2013-11-12 | closed | On Table Script |  | Change the start_date to Effective Start date as well as end_date to effective end date. This has to be followed for any HR (Navu Sir)
Change Version and Dcoument number Datatype | Required | 2013-11-13 | closed | On Table Script |  | Change Version and Dcoument number Datatype bcoz Version nujmber may be in 2.2.2 and Document number may be E/24523/00000111
Doc number | Required | 2013-11-14 | closed | On Table Script |  | Sequence number not needed | As Sequence number may change
Attribute can be limited to 10 numbers as table size is small | Required | 2013-11-15 | closed | On Table Script |  | Attribute Columns to be reduced to 10
Primary Key should be in first Field | Required | 2013-11-16 | closed | On Table Script |  | Primary Key should be in first Field
Sequence Name should be in prefix_column_name_suffix | Required | 2013-11-17 | closed | On Table Script |  | Sequence Name should be in prefix_column_name_suffix
Grant should be the same number of synonym | Required | 2013-11-18 | closed | On Table Script |  | Grant should be the same number of synonym
Fnd_users has to added in View from fnd_users | Required | 2013-11-18 | closed | On Table Script |  | Fnd_users has to added in View from fnd_users |  | Hav to confirm whether we can make it or not
Insertion into table with blob data type for documents | Required | 19/11/2013 | closed | On Create Page |  |  |  |  | 18/11/2013
Viewing of Documents like PDF whether Download or viewing from browser | Required | 20/11/2013 | Open | On User View Page |  |  |  |  | 18/11/2013
Parameterised search with Category and owning Department | Required |  | closed | On View Page
Update Page | Required |  | closed
Admin Functionlaity | Required |  | closed
Page Design to be changed as Doc No, version No, Dept, Cat, St date, End date |  |  | closed
Inserting on second table only while the user selects the checkbox |  |  | closed
Navigation back to search PG |  |  | closed
Spaces to be shortened and Page Desgin to be Even |  |  | closed
UpdateVersion-> Fields to be included & modified are Start Date, End Date, Version, File |  |  | closed
All should have same region |  |  | closed
Update Version Has to Be taken care |  |  | closed
Just have Department and Category instead of Owning |  |  | closed
Delete Functionality |  |  | closed
Creation PG Mandatory Fields -> Doc Name, Doc No, Eff Std |  |  | closed
Validation for time B/w ESD,EED |  |  | closed
File Size validation for upload size |  |  | Open
Number 0 validation for Doc No |  |  | closed
Doc No 10 chars |  |  | closed
Doc Name 200 chars |  |  | closed
(.) , (-) vali in Verison Number |  |  | closed
Dependent LOV in cat, dept |  |  | closed
Read/Accept Check |  |  | closed
Confimation on Read/Accept
Acceptance whether it is needed or not |  |  | closed
Update PG Region with Query
Effective start date and Effective End date should not overide when there is another version In other words for a working period you should have only one record. |  |  | closed
If It is to be overrided you must have to prompt the user to change the previous date |  |  | open
Change the view script with Effective Start and End date for Lookups , Enabled Flag, trunc(sysdate) |  |  | closed
Include a attibute "Must Read" |  |  | closed
Problem on Message Download |  |  | closed
Table gets freezed

## Sheet2
Doubts To be cleared

## Sheet3
Topic | Action Item | Target Date | Status | Location | Particular Location (Under) | Change | Remarks(On Open) | Remarks(On Closing )
Lookups Insertion | Required | 2013-07-10 | Closed
Insert update Delete Query statements | Required | 2013-07-10 | Closed
Making Changes in UI | Required | 2013-07-10 | Open
Making a New Tab | Required | 19/10/2013 | Open
Picture In Create Page | Required | 20/10/2013 | Open
Region Resizing | Required |  | Open
Back Button Disable | Required |  | Open
Position Applied For | Required | 21/10/2013 | Open | Recruit Page | Under Personal Information | LOV | Look up may be from Position Master table or use posapplLVO VO
Id Number Mandatory | Required | 21/10/2013 | Open | Recruit Page | Name | Mandatory to be changed | Marked to be mandatory or not after Confirmation
Address with Present and Peramanent as both | Required |  | Open | Recruit Page | Address | Need a Residential and Peramanent Address | Refer Cact Bank Project
ROP change | Required | 21/10/2013 | Open | Recruit Page | Status | To be Removed
Medical Done | Required | 21/10/2013 | Open | Recruit Page | Status | To be Removed
Interview Block has to be changed | Required |  | Open | Recruit Page | Interview Details Region | To be Redesigned | 1. All the Marks has to be removed. 2)Mode of Interiew(PopList)(Common Lookups).3) Level Field to be added(Lookup)(PopList) 4.Interview Time Range
Remarks to be taken out of Page and not from DB and have a Button called Evaluation Form | Required |  | Open | Panel PG |  | To Be created from Scratch | Remarks to be taken out of Page and not from DB and have a Button called Evaluation Form
Position Applied For (Look up types to be Entered) | Required | 21/10/2013
Created Tables, Views | Required | 23/10/2013 | Closed | Back End |  | Waiting for Authorisation | Changes made for int_mode, int_level, Eval_param
Page Creation (dependency) | Required | 24/10/2013 | Open | JDEV |  | Excel sheet creation of all elements
Page Creation -Qry Page | Required | 28/10/2013 | Open | JDEV |  | Page Creation